## PIVOT CONST
Development Team | STATUS
Linguistic | Not Started
Backend-eer | In Progress
Frontend-eer | Complete
Designer | Overdue
Secretary | On Hold
QA

## TEMPLATE
SPRINT 1 BACKLOG
STATUS: |  | Not Started
Maximum days: |  | 6
Total measuring |  | 0 |  |  | Sprint measuring after days
ID | Category | Sprint task | Implemented by | First measuring | 1 | 2 | 3 | 4 | 5 | 6
1 | Login Module | Task name | Staff | 0 | 0 | 0 | 0 | 0 | 0 | 0
2
3
4
5
6
7
8

## SPRINT - 1
SPRINT 1 BACKLOG
STATUS: |  | Complete
Maximum days: |  | 6
Total measuring |  | 57 |  |  | Sprint measuring after days
ID | Category | Sprint task | Implemented by | First measuring | 1 | 2 | 3 | 4 | 5 | 6
1 | Login Module | Workflow, Mockup & Wireframe | Designer | 13 | 8 | 5 | 0 | 0 | 0 | 0
2 |  | Frontend - Sign in page | Frontend-eer | 5 | 2 | 0 | 0 | 0 | 0 | 0
3 |  | Frontend - Sign up page | Frontend-eer | 5 | 5 | 3 | 0 | 0 | 0 | 0
4 |  | Frontend - Remember me logic | Frontend-eer | 3 | 3 | 3 | 0 | 0 | 0 | 0
5 |  | Backend - Models design | Backend-eer | 5 | 0 | 0 | 0 | 0 | 0 | 0
6 |  | Backend - Apis design | Backend-eer | 8 | 8 | 5 | 2 | 0 | 0 | 0
7 |  | Integrate Api | Frontend-eer, Backend -eer | 5 | 5 | 5 | 5 | 2 | 0 | 0
8 |  | Test | QA | 13 | 8 | 5 | 3 | 2 | 0 | 0

## SPRINT - 2
SPRINT 2 BACKLOG
STATUS: |  | In Progress
Maximum days: |  | 6
Total measuring |  | 52 |  |  | Sprint measuring after days | [5 empty] | STAFF MEASURING DEDAIL
ID | Category | Sprint task | Implemented by | First measuring | 1 | 2 | 3 | 4 | 5 | 6 | Designer | 15
1 | Navigation bar | UI Design | Designer | 2 | 0 | 0 | 0 | 0 | 0 | 0 | Frontend-eer | 19
2 |  | Frontend programming | Frontend-eer | 1 | 0 | 0 | 0 | 0 | 0 | 0 | Backend-eer | 18
3 | Reminders manager | UI Design | Designer | 5 | 0 | [5 empty] | QA | 13
4 |  | Frontend - Landing page | Frontend-eer, Designer | 8 | 8
5 |  | Frontend - Add new | Frontend-eer | 2 | 2
6 |  | Frontend - Modify | Frontend-eer | 2 | 2
7 |  | Frontend - Remove | Frontend-eer | 1 | 1
8 |  | Backend - Models | Backend-eer | 5 | 5
9 |  | Backend - Apis design | Backend-eer | 8 | 8
10 |  | Integrate apis | Frontend-eer, Backend-eer | 5 | 1 | 1 | 1 | 1 | 1 | 0
11 |  | Testing | QA | 13 | 13