## MAIN
PRODUCT BACKBOG
ID | As a … | I want to … | So that … | Priority | Sprint | Status
1 | End user | Login module | Create login module | High | 1 | Complete
2 | End user | Landing page that show today activities | Create landing page | Low | / | Not Started
3 | End user | Navigation bar | Create navigation bar | Medium | 2 | Complete
4 | End user | Page to manage reminders | Create reminder landing page for create, update and delete reminders | Medium | 2 | Overdue
5 | Developer | A module to automation tests | Write testing code and add it to npm commands | Medium | 2 | Overdue
6
7
8
9
10

## PIVOT CONST
ROLES | PRIORITIES | STATUS
End user | High | Not Started
Developer | Medium | In Progress
Manager | Low | Complete
--- |  | Overdue
On Hold